## Slide 1: PeopleSoft Financials 9.2 upgrade
Kick-Off Meeting

## Slide 2: AGENDA
Current Environment
Why Upgrade
New Environment
Samples Of 9.2 Advancements
Project Scope
Project Phases
Roles and Responsibilities
Project Timeline
Key milestones
Success factors
Risk factors
Communication
Next Steps (Fit/Gap Preparation)
FS 9.2 Kick-Off Meeting

## Slide 3: Current environment
Application
  Version 8.9
  Released: Summer 2005
  UMBC 8.9 Upgrade: 2/2006
  Last Bundle Released: 9/2011
  End of Oracle Support: 8/2013
Tools
  Version 8.53.27
  8.53 Released: 2/2013
  UMBC Upgrade: 12/2013
  End of Oracle Support: 7/2016

## Slide 4: New FEATURES!
Migrate to an Oracle supported application & tools release
Increased efficiency through performance enhancements improved usability, and streamlined processes.
Ease of maintenance post 9.2 using PUM (PeopleSoft Update Manager).
Adopt latest regulatory compliance features
Fully utilize features delivered in latest PeopleTools version.
Retire customizations for a lower cost of maintenance.
Leverage new set of development tools
Build a solid foundation to implement future UMBC Financials projects in PT pipeline
Ability to stay in compliance for patches and security & vulnerability updates as it relates to server software and operating system – Audit Risk
Improved Analytics
  (Reporting , Query, Pivot Grids, Composite Query, Drilling URLs, Charts , BI Publisher, etc.)
New Workflow Technology
Mobile Applications/Framework
People Tools Health Center (Performance Monitoring, Health of System, Review log files, etc.)
Cumulative Features by Module
Search Interface
Work Centers
Activity Guides
Dashboards
Fluid Pages
And many more………
Why Upgrade?

## Slide 5: NEW environment
Application
  Version 9.2
Tools
  Version 8.55

## Slide 6: GRANTS WORKCENTER

## Slide 7: GL WORKCENTER & Dashboard

## Slide 8: Journal ENTRY FLUID MOBILE APPROVAL

## Slide 9: ACTIVITY GUIDE - Contracts

## Slide 10: New Search framework

## Slide 11: PRIMARY Project scope
Upgrade PeopleSoft Modules 8.9 to 9.2 with minimal operational disruption
Leverage delivered functionality by retiring customizations as feasible within project timeline
Eliminate dormant UMBC modified reports/processes/functionality
Retrofit approved customizations
General Ledger | Contracts
Asset Management | Grants Management
Receivables | Payables
Billing | Purchasing
Projects | Commitment Control

## Slide 12: PRIMARY Project scope
Crystal Reports conversion
nVision conversion
Transition local infrastructure (Application, Database, and Web Servers) to Amazon Web Services
Special Projects
Archiving expired Grant data
Analysis and rewrite of GL State Interface

## Slide 13: SECONDARY PROJECT SCOPE
Evaluate 9.2 impact in conjunction with pre-existing PT project requests
Identify features/tools that may be utilized post upgrade
Examples:
Change Order/PO notifications
Effort reporting notifications
Expense reimbursement workflow
Introduce new functionality if primary objectives have been met, and feasible within project timeline

## Slide 14: project phases
Planning
Testing Cycles
(Training)
Deploy and Optimize
Analyze & Design
Configure & Develop
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
Project Management

## Slide 15: planning
Set the foundation for a successful upgrade
Establish tools and standards used throughout the upgrade project
Establish project scope and related requirements
Build technical environments and begin initial pass
Learn about PeopleSoft 9.2
Fit/Gap preparation
Phase 1

## Slide 16: ANALYZE AND DESIGN
Provide functional staff with a 9.2 upgraded copy of production and 9.2 Demo
Conduct Fit/Gap meetings for each module or business area
Create functional specification documents For 9.2 modifications
Special project meetings to gather requirements
Phase 2

## Slide 17: FIT/GAP Explained
Task to formally determine how system meets or fails to meet business requirements.
Likely facilitated through meetings to analyze and compare current business practices and requirements with PeopleSoft “delivered” functionality in 9.2
Fit: A business requirement met using delivered System functionality.
Gap: A business requirement that isn’t met using delivered functionality.
Identifies areas that may require additional analysis to determine best Fit to specific institutional requirements.
Provides refinement to specific project task and scope for Project Plan.
Will lead to development of functional specifications
Identify pre-existing customizations that may be replaced with delivered functionality
Be prepared to discuss current business processes, reporting needs, required interfaces, applicable laws, regulations, and security requirements.
Phase 2

## Slide 18: Configure and develop
Review and configure set up pages for all modules
Configure/Alter security settings
Document new/updated business processes
Create/Update technical specifications
Create/Update new test scripts
Retrofit approved customizations, interfaces, processes, and reports
Crystal report / nVision conversion
Development and configuration of special projects
Execute test pass to create initial testing environment
Phase 3

## Slide 19: Testing Cycles & training
Unit - Testing after completion of retro-fits and customizations. Test Scripts not required initially.
System – Testing by Functional Area leaders using new test scripts
Integration – Using Integration Broker CS and HR , Third Party Interfaces
User Acceptance – Bigger group of Functional Testers involved, test production-like security
Performance – Testing targeted processes for performance. Process large amounts of data.
Regression – Retesting if previous tests failed
Develop training materials needed for user acceptance testing (and beyond)
Phase 4

## Slide 20: deploy and optimize
Perform readiness assessment
Develop cutover plan and any contingencies
execute and optimize practice production passes
Obtain approval for “Go Live” weekend
Execute production upgrade
Provide production support
Perform performance monitoring and database tuning
Phase 5

## Slide 21
Roles and responsibilities
Executive Stakeholders
  Set objectives
  Provide guidance
  Remove obstacles
  Oversee project budget
Project Managers
  Develop project plan
  Coordinate resources
  Oversee project and timeline
  Provide scope management
  Facilitate meetings with team members to discuss progress and issues
  Work with tech. team to develop “Go-Live” checklists
  Identify project risks
  Establish change control procedures and standards
  Communicate project updates, planning, and procedures
Ben Lowenthal
Joe Kirby ...
Tony Finneran
Stacy Long
Sasha Hudson

## Slide 22
Roles and responsibilities
Functional Project Leaders
  Work directly with functional area leads for each module
  Lead Fit/Gap sessions
  Lead Set Up and configuration for each module
  Coordinate test cycles
  Determine acceptance of new release
  Review Release Notes and cumulative features
Functional Area Leads and Subject Area Experts
  Provide business processes and requirements
  Review Release Notes and cumulative features
  Transfer knowledge to staff per each module/area
  Conduct and participate in Fit/Gap meetings
  Make design decisions and develop design documents
  Help configure Set Up pages
  Create and execute Test Scripts/Procedures
  Report & document issues
  Assist Tech Developers to resolve issues
  Train Acceptance Testers
  Ensure business needs are met
Consultant (TBD)
Sasha Hudson
Linda Rothfus | Sue Maltby
Margo Falahee | Tim Kuonen
Aimee Howell | Gregory Saba
Albert Smith | Joanna Napoli
Tina Carter-Brown | Gayle Chapman
Mallela Ralliford | Melissa Diehl
Marlo Zeroth | Consultant
Jacqueline Brown | 
Rebecca Stuckmeier | 
Sharon Stankovic | 

## Slide 23
Roles and responsibilities
Technical Upgrade Team
  Installation and Configuration of Upgrade Tools
  Installation of Demo Environment 9.2
  Execute Upgrade Passes
  Apply Required Updates, Fixes, and Patches
  Perform System Backups
  Assist with Database Performance/Tuning
  Perform Security Configuration/Changes
  Troubleshoot Technical Issues
  Ensure Data Integrity
  Transition Servers to Amazon Web Services
  Manage Login, Security, Roles, Etc.
  Configure Broker, Workflow, Process Monitor
Technical Developers
  Troubleshoot Technical Issues
  Develop and Retro Fit Reports, Queries, Interfaces, Processes, and PeopleSoft Objects.
  Perform Unit Testing
  Lead Analysis and Design of Special Projects
  Analyze Compare & Audit Reports
  Document Technical Specifications
  Become Familiar with New Tools/Technology
Tony Finneran
Stacy Long
Todd Haddaway
Damian Doyle
Jeremy Gude
Steve Ostrove
Chris Sutherin
Lance Rand
Derek Harley
David Sylva
Consultant (TBD)

## Slide 24: Critical success factors
Senior Management Sponsorship
Staff resources focused and committed to project
Project planning
Define and adhere to scope
Project Team empowered to make decisions
Open and effective communication
Knowledge transfer
Timely decision making
Follow standards and procedures for change management

## Slide 25: risk factors
Production issues may impact availability of both functional and technical team members
Technical resource team is limited
Process of hiring consultant(s) delayed
Amazon Web Services not ready for full system test, or experience integration/communication/Performance issues
Total execution time to perform upgrade steps (Passes)
Project scope creep
Competing projects
Data migration issues from 8.9 to 9.2
Learning curve for new technology

## Slide 26: Communication Tools
myUMBC group:
  Campus - http://my.umbc.edu/groups/fs92-campus
Utilize existing listservs for updates/announcements
Town Hall Meetings
Business Manager meetings
Weekly project team meetings
Track and update project in PT
  Will include effort/status reports
Update and manage the project plan, which is linked to PT project
RT dedicated queue for Finance upgrade issues